## doc-history
RELEASE | DATE | DESCRIPTION
r1 | 18.04.2022 | initial release

## Non-functional requirements
Release 1
1 | No user authentication/authorization support yet, anyone can use the system.
2 | Use UTF-8 as character-encoding
3 | The server must be assessible from KMUTT network (but not limited to).

## Product Backlog
Sort | PBI NAME | PBI DESCRIPTION / CONDITIONS | Type | Priority | Size | Sprint
1 | VIEW-EVENT-LIST-EMPTY | 1. There is no event scheduled in any event category. 2. Display 'No Scheduled Events'. | Must-have | 1 |  | 1
2 | VIEW-EVENT-LIST-ALL | 1. There are scheduled events. 2. Display all scheduled events. 3. In each event, display: event date, event start time, event duration (in minutes), eventCategoryName, bookingName (ชื่อการจอง) 4. The list is sorted in descending order on event date/time. (เรียงลำดับจากวันเวลาของกิจกรรม จากอนาคตมาอดีต) | Must-have | 2 |  | 1
7 | VIEW-EVENT-DETAILS-BASE | 1. Event is not null. 2. Display: event date, event start time, event duration (in minutes), eventCategoryName, bookingName (ชื่อการจอง), bookingEmail, eventNotes | Must-have | 3 |  | 1
8 | SCHEDULE-EVENT-BASIC-NO-VALIDATION | 1. The user can schedule a new event by specifying : eventCategory, bookingName, bookingEmail, eventStartTime, eventNotes (optional) 2. The system uses eventCategoryDuration of the specified eventCategory as eventDuration. 3. No input validation. 4. Assume that the input from user is valid. | Must-have | 4 |  | 2
9 | CANCEL-EVENT-BASIC-SUCCESS | 1. The user can cancel any event. 2. The system must ask user for confirmation. 3. The event is deleted from database after the operation. | Must-have | 5 |  | 2
10 | RESCHEDULE-EVENT-BASIC-NO-VALIDATION | 1. The user can edit any event. 2. The user can edit eventStartTime and eventNotes only. 3. No input validation. 4. Assume that the input from user is valid. | Must-have | 6 |  | 3
12 | VALIDATE-DATETIME-FUTURE | 1. Validate date/time during scheduling and rescheduling that the start date/time is in the future. | Should-have | 7 |  | 3
14 | VALIDATE-EMAIL | 1. Validate e-mail specified during scheduling an event that it is an e-mail. | Should-have | 8 |  | 3
13 | VALIDATE-DATETIME-NONOVERLAP | 1. Validate date/time during scheduling and rescheduling that the start and end date/time of the event is not overlapped with other event in the same event category. | Should-have | 9 |  | 3
11 | CONFIG-EVENT-CATEGORY | 1. The user can edit any event category. 2. The user can edit any event category field. 3. The change to eventCategoryDuration is applied to new event only. 4. The change to eventCategoryName or eventCategoryDescription is applied to any event under the specified category. 5. No input validation. 6. Assume that the input from user is valid. | Could-have | 10
15 | VALIDATE-EVENT-CATEGORY-NAME | 1. Validate eventCategoryName during configuring of event category that it is unique. | Could-have | 11
16 | VALIDATE-DURATION | 1. Validate duration specified during configuring of event category that it is an integer between 1 and 480. | Could-have | 12
4 | VIEW-EVENT-LIST-CATEGORY | 1. User can filter events by event category. 2. If there is no event scheduled in the specified event category, display 'No Scheduled Events'. 3. If there are scheduled events on the specified event category, display each event as in 'VIEW-EVENT-LIST-ALL'. 4. The list is sorted in descending order on event date/time. (เรียงลำดับจากวันเวลาของกิจกรรม จากอนาคตมาอดีต) | Could-have | 13
5 | VIEW-EVENT-LIST-UPCOMING | 1. User can filter events by date/time, show only future and on-going events. 2. If there is no on-going or future event, display 'No On-Going or Upcoming Events'. 3. If there are on-going or future events, display each event as in 'VIEW-EVENT-LIST-ALL'. 4. The list is sorted in ascending order on event time. (เรียงลำดับจากเวลาของกิจกรรม จากน้อยมามาก) | Could-have | 14
6 | VIEW-EVENT-LIST-PAST | 1. User can filter events by date/time, show only past events. 2. If there is no past event, display 'No Past Events'. 3. If there are past events, display each event as in 'VIEW-EVENT-LIST-ALL'. 4. The list is sorted in descending order on event date/time. (เรียงลำดับจากวันเวลาของกิจกรรม จากใกล้วันเวลาปัจจุบันไปไกล) | Could-have | 15
3 | VIEW-EVENT-LIST-DAY | 1. User can filter events by date/time, show only the events with eventStartTime as specified date. 2. If there is no event scheduled on the specified date, display 'No Scheduled Events'. 3. If there are scheduled events on the specified date, display: event date, event start time, event duration (in minutes), bookingName (ชื่อการจอง) 4. The list is sorted in ascending order on event time. (เรียงลำดับจากเวลาของกิจกรรม จากน้อยมามาก) | Could-have | 16

## Attributes
event
Attribute Name | Description
bookingName | ชื่อในการจอง ขนาดไม่เกิน 100 ตัวอักษร เช่น Somchai Jaidee Group 04
bookingEmail | e-mail ของผู้จอง เช่น somchai.jai@kmutt.ac.th
eventCategory | ระบุว่าการจองนี้อยู่ภายใต้หมวดหมู่การจองใด เช่น Project Management Clinic
eventStartTime | วันเวลาเริ่มต้นของนัด เช่น 26 April 2022 13.30
eventDuration | ระยะเวลาของนัด เลขจำนวนเต็ม หน่วยเป็นนาที กำหนดโดยผู้จัดใน event category (ผู้จองไม่สามารถเลือกได้) เช่น 30 (นาที)
eventNotes | Optional, ข้อความจากผู้จองถึงผู้จัด ขนาดไม่เกิน 500 ตัวอักษร เช่น ปรึกษาเรื่องการแบ่งงาน
event category
Attribute Name | Description
eventCategoryName | Unique, ชื่อหมวดหมู่การจอง ขนาดไม่เกิน 100 ตัวอักษร เช่น Project Management Clinic
eventCategoryDescription | Optional, คำอธิบายหมวดหมู่การจอง เพื่อแจ้งให้ผู้จองทราบ ขนาดไม่เกิน 500 ตัวอักษร
eventDuration | ระยะเวลาของนัดสำหรับการจองในหมวดหมู่นี้ ใช้ตอนสร้างการจองใหม่ เลขจำนวนเต็ม หน่วยเป็นนาที มีค่า 1-480 นาที เช่น 30 (นาที)